Software Configuration Management Plan

| Name of project: SIPAE | Version: 1 |
| --- | --- |
| Owner: Yareli Vanessa Flores Vizcaíno | Author: Yareli Vanessa Flores Vizcaíno |
| Date of creation /update: February 28, 2020 |  |

# Changes Request (CH)

| Title | CR-1: GPS localization of missing students |
| --- | --- |
| Description | The client requests that the system incorporates an app that will be installed on students’ mobile phones for spotting their presence if they are not located within the school premises. If the students are to far from school premises (more than 100 meters) within school hours, the student cellphone will send a message to both school administration and his/her tutor. |
| Required changes with regards the team | Hire an extra programmer. |
| New activities for Human Resources (HR) | Extra programmer: -All modules for mobile app / students |
| Cost of the CR | $115 / hour -> 15 days: 6hrs = $10,350.00 |
| How much will be affected the duration of the project | This CR won’t change the duration of the project because when hiring an extra programmer, their own tasks will be assigned. |
| Do we have enough human resources to apply the CR? | We don’t have, is necessary hire an extra programmer. |
| Is the CR mandatory by Law? | No |
| How will be improved the System due the CR? | Yes, if implementing this CR parents will have one more tool to know about their children. |

| Title | CR-2: Double-checked entry- exit registration |
| --- | --- |
| Description | Due it was found that several students checked the entry of other students that wanted to wander instead of attending their courses, the administration wants to incorporate additional biometric measures for grating the access or exit of students. |
| Required changes with regards the team | Assign new tasks to developer 1, designer and tester 1. |
| New activities for Human Resources (HR) | Developer 1 -> Develop module for register entry/exit with biometric measures Designer -> Add the changes to documentation of project Tester -> Design and implement test for the new module |
| Cost of the CR | Developer 1 -> 7 days/6 hrs. = $4,830.00 Designer -> 2d = $1,200.00 Tester 1 -> 2d = $1,116.00 Total: $ 7, 146.00 |
| How much will be affected the duration of the project | 2 weeks more |
| Do we have enough human resources to apply the CR? | Yes |
| Is the CR mandatory by Law? | No |
| How will be improved the System due the CR? | Yes, the entry module will be safer with this CR because students will have to identify for register the entry. |

| Title | CR-3: Special cases for students’ monitoring due public policies |
| --- | --- |
| Description | The government requests that all personal data produced in schools not concerning to grades and diplomas should be destroyed after the student graduates or he/she drops the school. Besides, a new policy concerning all academic levels at the country reports the statistics of students learning, student misconduct, alcohol and drugs addiction at the school by year. For previous reasons, there is a need for creating a module that tracks the statistics and erases all the behaviour records for alumni and dropout students. |
| Required changes with regards the team | Assign new tasks to developer 1, designer and tester 1. |
| New activities for Human Resources (HR) | Developer 1 -> Modify attendance module, modify exit permits, modify entry module, remove report module. -> Connection to the API governmental for shows information about student misconduct. Designer -> Add new items to documentation for every module modify or remove. Tester 1 -> Design and implement new tester for every module modify. |
| Cost of the CR | Developer 1 -> 15 days/6 hrs. = $10,350.00 Designer -> 7d/6hrs = $4,200.00 Tester 1 -> 7d/6hrs = $3,906.00 Total: $ 18,456.00 |
| How much will be affected the duration of the project | 22 days more |
| Do we have enough human resources to apply the CR? | Yes |
| Is the CR mandatory by Law? | Yes |
| How will be improved the System due the CR? | It won’t go against the law |